## Slide 1: Semester Project: Topics Areas, Requirements, and Deadlines

## Slide 2: Grade Distribution
Proposal: 20%
Preliminary Deliverable: 40%
Final Demo: 40% (50% successful completion of list of deliverables, 50% evaluation by judges)

## Slide 3: Project Proposal and Important Dates
The project proposal should include the following:
1. Description of the specific project (Fine Motor Skills Training, Education, Assistive Technology, Healthcare Applications of VR Rehabilitation/Therapy).
  You should describe the goals and methods of your proposed project in enough detail to convince me that you can really finish it before the end of the semester.
  The choice of tools (software and hardware) that you will use for the project.
2. Three separate lists of deliverables:
Project proposal presentation and workload distribution – Monday, Sept 24th and Wednesday, Sept 26th
    Final detailed task list for Preliminary Deliverable due date: 5pm, Wednesday Oct 3rd
  Exactly what you will have ready as the preliminary deliverable 2 – Thursday Oct 18th and Friday Oct 19th
    Final detailed task list for Final Deliverable due date: 5pm, Wednesday Oct 24th
  Exactly what the final deliverables will be – In Class 11/26 through 12/5, with a panel of judges, and peer assessment.

## Slide 4: Project Proposal and Important Dates
3. Grading criteria for each list of deliverables based on a 100-point scale for each member of the group.
  You should tell me exactly how I should grade you if you deliver only a part of what you have proposed.
  A good approach is to give me a list of objective milestones for your project and assign some number of points to each milestone you achieve.
  Please specify what part of the project each person is responsible for and give me separate grading criteria for each group member.
  A good method of breaking down points is to subdivide your part of a deliverable by 7 to 10 steps that can be objectively verified and assigning points to them, adding up to a total of 100 points for each person per deliverable.
Maximum time limit for each proposal presentation will be 10 mins/group. All the details of each project proposal must be approved by the TA before October 3rd before they become final.

## Slide 5: Project Expectations Criteria for Grading Final Demo
Immersion/Engagement (20%) – Stereo, motion parallax, size and scale of objects rendered to appear realistic. If on a mobile app, then providing an immersive viewing experience using the google cardboard. Otherwise, to what extent is the VR system engaging to the user (visual and behavioral realism) .
Natural 3D Interaction and Multi-modal Feedback (20%) – Examples include:
    Input: Using speech, gesture, touch, spatial input device (3D Interaction), integrating motion etc.
    Output: Rich visual cues, spatial auditory cues, haptic/pseudo-haptic feedback, virtual human verbal and non-verbal behaviors etc.
Interactive Scenario Design and Generation (40%) – Rich virtual environment scene, task or goal oriented interactive scenario between user and system, rich user experience and narrative. Each project should consist of the following scaffolded learning scenario:
  Instruction Phase: The VR system instructs the user on the scenario to expect and how to accomplish the task in virtual reality.
  Guided Practice: The VR system gives at least 2 “scaffolded” guided practice in the training/education/therapy/rehabilitation task, monitors to the user’s input, and interactively provides real-time guidance if the user is not performing correctly, and to guide to the user to successfully accomplish the task.
  Open Exercise with post-hoc feedback: The VR system provides at least 2 open exercises in the task for the user, and provides summative feedback with an objective score and feedback on how well the user accomplished the task without any real-time interactive guidance.

## Slide 6: Basic Expectations
4. Formative and Summative Evaluation (20%) – Conduct a simple usability study with your system to evaluate the usability (usefulness, user experience, ease of use, satisfaction, task performance – efficiency and effectiveness, frustration, presence/co-presence) of your VR system with at least 5-10 participants, who are target users of your system. Create surveys and gather data from potential users of your system, and document it for presentation on the final deliverable demo.

## Slide 7: Collaborators
Public Health Application
Dr. Lingling Zhang
Assistant Professor
Department of Nursing
University of Massachusetts Boston
Email: lingliz@clemson.edu
Assistive Technology
Ms. Margaret Camp
Director of Student Accessibility Services
Heathcare practitioner education and patient centric applications
Dr. Tracy Fasolino
Associate Professor
Email: tfasoli@clemson.edu
Clemson Counseling and Psychological Services
Redfern

## Slide 8: Previous Projects
See PDFs of Project Flyers Attached.

## Slide 9: VRS Fall 2013

## Slide 10: VRS Fall 2015

## Slide 11: Fall 2015